## Slide 1
The main extension of Mustang Rock connecting to the parking lot has been poured.
NEW ADMINISTRATION BUILDING

## Slide 2
The building location is outlined by the iron piers. The Board room is located in the bottom left and finance is in the top right of the photo.

## Slide 3
The storm water connection has been completed on the western side of the site.

## Slide 4
The building wall concrete structure in the superintendent, operations, and finance office areas has been completed. Excavation of the grade beams is progressing.

## Slide 5
CMU storage buildings and restrooms are in progress. The roof on the pressbox has been completed.
BOSWELL HS

## Slide 6
The weight room glass wall has been installed. Moisture conditioning of the remaining structure has been completed.
Pier drilling has begun on the visitor bleachers and is expected to be completed on August 30, 2021.

## Slide 7
This photo shows the pier rebar for the visitor bleachers has been tied together.

## Slide 8
LAKE COUNTRY ES
Installation of the columns for the bus canopy has begun. Plaster on the top floor of the exterior of the building is near completion.

## Slide 9
Finish lighting has been installed in the library.
Main foyer is receiving final coat of paint.

## Slide 10
Area 2 hallway sheetrock has been installed.
Cafeteria lighting and ceiling have been completed. Ceiling grid in area 1 is in progress.

## Slide 11
Bathroom partitions have arrived on site and are being installed. Roof panels have arrived and are waiting for installation. Area 6 classrooms are sheetrocked with tape and bedding in progress.

## Slide 12
Baseball/Softball Turf Projects at Chisholm Trail HS and Saginaw HS -
Hellas has mobilized on site and has begun excavation and moisture and conditioning. Chisholm Trail HS construction entrances are installed at both the baseball and softball fields. Earthwork has begun at the baseball field. Saginaw HS baseball and softball fields construction entrance installations are in progress.
OTHER PROJECTS